## Sheet1
Hardware & Equipment Management System |  |  | Stages
PROJECT MEMBERS
| Planning | Analysis & Requirements | Design | Development | Integration & Testing | Implementation | Operations & Maintenance | Total
| (58 Days) | (12 Days) | (66 Days) | (40 Days) | (17 Days) | (33 Days) | (10 Days) | Time
Kent Curato | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 1,888 Hours
(Project Manager) | 58 Days | 12 Days | 66 Days | 40 days | 17 Days | 33 Days | 10 Days | 236 Days
Albert Mojica | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * |  | 2.0 Hours* |  |  | 1,108 Hours
(System Designer / Quality Assurance) | 58 Days | 12 Days | 66 Days |  | 10 Days |  |  | 146 Days
Mark Mondejar | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 1,888 Hours
(System Programmer 1) | 58 Days | 12 Days | 66 Days | 40 days | 17 Days | 33 Days | 10 Days | 236 Days
Sebastian Ebreo | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 8.0 Hours * | 1,888 Hours
(System Programmer 2) | 58 Days | 12 Days | 66 Days | 40 days | 17 Days | 33 Days | 10 Days | 236 Days
Total Time | 1,856 Hours | 384 Hours | 2,112 Hours | 960 Hours | 428 Days | 792 Hours | 240 Hours | 6,772 Hours